## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
O02 | Different types of memberships | As a gym owner, I want to provide several different types of memberships. So that I can provide different types of functions to them. | Very High | 1 | 1. Membership should be divided into ordinary members and VIP members. 2. Ordinary members and VIP members have different functions. |  | March.30th | April.13th
O02a | Ordinary member functions | As a gym owner, I want to provide video courses to all members. So that both ordinary members and VIP members can learn it. | Very High | 1 | 1. Ordinary members can watch video courses. 2. VIP members can watch video courses. |  | March.30th | April.13th
O02b | VIP member privileges | As a gym owner, I want to provide live training with a personal trainer to VIP members. So that only VIP members have the privilege of live training. | Very High | 1 | 1. VIP members can participate in live training. 2. Ordinary members cannot participate in live training. |  | March.30th | April.13th
B01a | Choose training levels | As a fitness beginner, I want the application to offer training materials in different levels. So that I can choose within my capability. | Very High | 1,2 | 1. Training materials should be divided into different levels. 2. Users can choose from levels in certain mode. | 3 Levels. | March.30th | Apirl.23th
C01 | Easy maintainess | As a code writer, I want to have a software system that is easy to manage and maintain. So that I can save time and improve efficiency. | Very High | 1,2,3,4 | 1. The code writer knows the function of each part of the code. 2. The relationship betwwn classes is clear and doesn't cause ambiguity. |  | March.30th | May.29th
U01 | Register & login | As an application user, I want to have an easy access to register and login. So that I can create my own account and enter it. | Very High | 1 | 1. When entering the app, an login interface should be displayed. 2. In this interface, new users can also register. |  | March.30th | April.13th
U02 | Change password | As an application user, I want to have an easy access to password changing services. So that I can ensure my account safety. | Very High | 1 | There should also be an access to change the password at the login interface. |  | March.30th | April.13th
M01 | Manger display | As a manager of the membership, I want to have an interface where I can clearly see the type of membership and other information. So that I can manage users better. | Very High | 1 | 1. The application has a specific UI for manager. 2. All members with their information should be displayed clearly at the interface. |  | March.30th | April.13th
O03 | Live training schedule | As a gym owner, I want to have live training schedules for trainers. So that VIP members can only book live training during the trainer's free time to avoid time conflicts. | Very High | 2 | 1. Set schedules for trainers who offers live training. 2. Users can only book live sessions during the trainer’s free time. 3. Booking information should be stored in a file. |  | April.14th | April.23th
P02 | Interact with trainers | As a user proficient in gym, I want to contact with trainers on my targets and physical abilities. So that trainers can design specific exercises for me. | High | 3 | When the user books a live session, the detailed information of the user can be sent to the trainer. |  | April.24th | May.22th
B02 | Introduction & instructions for training item | As a fitness beginner, I want the application shows brief introduction and instructions for each training item. So that I can know whether I need and how can I practice | High | 1 | 1. Verify that there are relating words or sentences to describe the training item in the choosing interface. 2. Make sure that clear and accurate instructions will be given for each training item. |  | March.30th | April.13th
O01 | Membership distinction | As a gym owner, I want to ensure that different type of users have differnet access permission to different sections. So that the function can be used by appropiate user group. | High | 3 | Verify that the system can distinguish user type according to the log in information and set different access based on it. |  | April.24th | May.22th
O04 | Membership attraction | As a gym owner, I want that the application offers some discount. So that we can always attract customers. | High | 3 | There should be a discount offered when topping up for the first time. |  | April.24th | May.22th
U02 | User information update | As an application user, I want that it will be possible for me to change some of my user information. So that I can update my newest physical conditions or personal preferences. | High | 1,2 | 1. There should be a UI that displays some of theie personal information for users to check. 2. Users should be able to make some changes within that interface. |  | March.30th | Apirl.23th
O05 | Add courses | As, a gym owner, I want to be able to add new course. So that the gym can respond quickly to changes in user preferences. | Medium | 2 | 1. New courses can be added by the administrator. 2. Price, classification and other information can be defined by the administrator. | Embodied in both administrator interface and user interface. | April.14th | April.23th
P03 | Cancel a booked live session | As a user proficient in gym, I want to cancel the live classes before the start time. So that I can have a better user experience. | Medium | 2 | An obvious button for cancel should be displayed in the interface of booking lessons. |  | April.14th | April.23th
T01a | Member information | As a personal trainer, I want to know exactly the member’s targets and physical abilities. So that I can have a better design of my teaching content and service for my members better. | Medium | 3 | 1. The member's physical information is stored in a file. 2. The member has a clear training objectives. |  | April.24th | May.22th
U03 | Sign up hint | As a user, I want to be noticed if I input some illegal characters or violate naming rules. So that I can sign up easily. | Medium | 2 | When user input illegal characters or violate naming limits, the system should give user some feedback. |  | April.14th | April.23th
U04 | Reset password | As a user, I want to be able to reset my password using my ID and Email. So that I can continue to use my account even if I forget my password. | Medium | 2 | 1. There is a reset password choice in the login interface. The user can enter into change password interface by clicking it. 2. The user can input his/her ID and Email to begin resetting password if the ID and Email are related. |  | April.14th | April.23th
U05 | Membership upgrade for user | As a user, I want to be able to have an access to membership upgrade. So that I can enjoy better services. | Medium | 2 | 1. There should be a membership upgrade choice at personal display interface. 2. There should be access to more services after upgrading. |  | April.14th | April.23th
M02 | Information update for manager | As a manager, I want to be able to see information updates for each user. So that I can know and manage users and the whole gym system better. | Medium | 2 | 1. Manager display interface should have different lists for different types of user. 2. When user make changes to his/her personal information, it should be also visible for the manager. |  | April.14th | April.23th
C02 | Software logic | As a code writter, I want the software interface to be logical. So that users can quickly learn how to use it. | Low | 4 | User interface hierarchy is clear. | Have a navigation bar. | April.14th | April.23th
C03 | Interface aesthetics | As a code writter, I want the software to be beautiful and user-friendly. So that it can be in line with the user's preferences. | Very low | 4 | 1. The software interface is beautiful. 2. The software interface is in line with users' preferences. |  | May.23th | May.29th